## Gantt Chart
Speed Typing Gantt Chart
PROJECT TITLE |  | Speed Typer |  |  |  |  | COMPANY NAME | [6 empty] | The Programmers
PROJECT MANAGER |  | Andrew Denegar and Jack Holy |  |  |  |  | DATE | [6 empty] | 2024-09-04
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Create Basic "Hello World" app |  | 2024-09-04 | 2024-09-06 | 2 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Create draft program diagram |  | 2024-09-04 | 2024-09-06 | 2 | 0% | bar: WEEK 2 W
1.2 | Design Database | Andrew | 2024-09-06 | 2024-09-11 | 5 | 0% | bar: WEEK 2 W to WEEK 3 W
1.3 | Create a Database | Andrew | 2024-09-06 | 2024-09-13 | 7 | 0% | bar: WEEK 2 R to WEEK 3 R
1.4 | Create a basic HTML page with CSS | Jack | 2024-09-06 | 2024-09-13 | 7 | 0% | bar: WEEK 3 M to WEEK 3 R
1.5 |  |  |  |  | 0 | 0% | bar: WEEK 3 T to WEEK 3 R
1.6 |  |  |  |  | 0 | 0% | bar: WEEK 3 F
2 | Project Definition and Planning
2.1 | Scope and Goal Setting |  |  |  | 4 | 0% | bar: WEEK 4 M to WEEK 4 R
2.2 | Budget |  |  |  | 3 | 0% | bar: WEEK 4 F to WEEK 5 F
2.3 | Communication Plan |  |  |  | 0 | 0%
2.4 | Risk Management |  |  |  | 0 | 0%
3 | Project Conception and Initiation
3.1 | Status and Tracking |  |  |  | 0 | 0%
3.2 | KPIs |  |  |  | 0 | 0%
3.2.1 | Monitoring |  |  |  | 0 | 0%
3.2.2 | Forecasts |  |  |  | 0 | 0%
3.3 | Project Updates |  |  |  | 0 | 0%
3.3.1 | Chart Updates |  |  |  | 0 | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives |  |  |  | 0 | 0%
4.2 | Quality Deliverables |  |  |  | 0 | 0%
4.3 | Effort and Cost Tracking |  |  |  | 0 | 0%
4.4 | Project Performance |  |  |  | 0 | 0%